## Slide 1: Sprint Transitions
Software Process

## Slide 2: Sprints (Review)
Sprints will be three weeks long, starting tonight
The last Tuesday of each sprint will be pre-planning for the next sprint
The first Tuesday of each sprint will be planning for that sprint
  Also retrospective for the previous sprint
Multiple “Standup” meetings each week
Companies will use some variation of this process, but nothing is standard and everywhere is a little different (this can be a good thing!)

## Slide 3: Sprints (Review)
Sprint 1 (2-4 weeks long)
Sprint 2 (2-4 weeks long)
Pre-Planning Sprint 1
Pre-Planning Sprint 2
Pre-Planning Sprint 3
Planning Sprint 1
Planning Sprint 2
“Standup” Meetings
“Standup” Meetings
Your team is expected to have at least one “Standup” outside of class each week

## Slide 4: Pre-planning Meeting (review)
Overview of sprint priorities
  This is done by the PM
  Not “just a list of PBIs”; what is the end goal of the sprint? What happens if things need to be cut? What happens if there is extra time in the sprint?
Expected work to carry forward
Update calendar with time off
Stories from backlog - Assign stories to individuals to be estimated over the week

## Slide 5: The Scrum Meeting “Standup” (Review)
Run by the Scrum Master
Normal work environments have these usually once a day
  Sometimes called “Stand-Up”, because they should be brief
  Scrum master keeps the meeting on track – watch for too many details
Each engineer will record time against active tasks
  Scrum master makes the edits in real-time
Discuss blocking issues or slipping tasks
PM is attentive to possible bottlenecks and critical path issues
Check the burndown at least once a week
  Make the burndown “look good”
  PM decides what tasks will get bumped if needed

## Slide 6: Sprint Planning Meeting
Agenda
  Retrospective and Demos
  Taskify
    Assign tasks to each person
  Leveling
    Make sure each person is approximately in balance for their capacity
During the meeting, estimates and tasks are discussed
  Does the list of tasks match the acceptance criteria?
  Does the team agree with the task estimates?
  Are there tasks that belong in another PBI?
If your pre-planning meeting and week went well, then sprint planning is easy! Otherwise, not so much…

## Slide 7: Sprint Retrospective
Demos
  Show off your features to your peers, PM, and manager
How we did
  Led by the Product Manager
  Highlights and Lowlights
What worked well and what didn’t go well
  Around the room taking turns
  Scrum master records these for future reference and work
  Process changes for the team (probably not much for this class)